## Appendix F – Design Process

Implementation Process

Planning and Design Guidelines

(Deliverable dates to be added by TRRP)

## Design Team Meeting Schedule

- Full two day meeting. Review and make recommendations on concepts for initial Phase II project

sites. Discuss development of Design Guide by HVT

- Full two day meeting. Conceptual Design reports for Phase II project sites due with formal

presentation from each design group and Phase II Float

- Full two day meeting. Discuss VE Study results, Riparian Designs, and design workshop

- Full two day meeting. Draft Engineering Design reports for Phase II project sites due with formal

presentation from each design group and design workshop. Discuss and distribute the next phase

II project sites to design groups

## Initial Site Evaluations and Recommendations – All Design Team Members and Program Partners

## (DT)

- Site selection

- Multi-Disciplinary Design Groups members identified / selected for each site

- Identify baseline existing topography to be used and areas of concern

- Identify baseline hydraulic model to be used and additional data needs.

- Identify known infrastructure and Archeological constraints, bedrock, and valley confinement

from air photo. It is important to identify project stopping hurdles early on.

- Bureau of Reclamation data collection needs

- Right of Entry (ROE) based on potential site access and extent of Environmental Study Limit (ESL)

- Test pit and piezometer locations indicated on air photo

- Primary survey control locations identified

## Existing Conditions Data Collection – USBR and/or Contractor

- Landowner Rights of Entry (ROE) to access their property for surveys and other data collection

needs, including any important instructions for access. Completed by USBR.

- Archeological clearance for the project site. Completed by USBR or contractor.

- Primary survey control point values to establish vertical and horizontal control during design data

collection. Completed by DWR.

- Existing conditions topography from 2016 LiDAR DTM or most recently approved Lidar DTM product and other existing conditions base layers. Completed by USBR and contractor.

- Geological Investigation report including information on substrate characteristics, bedrock elevation,

groundwater elevation, and piezometer locations. Completed by USBR. Available from TRRP website - Document and Data Library.

- Design Process for each Multi-Disciplinary Design Group –

## Conceptual Design Phase (30% Design)

- On-Site Planning and Reconnaissance

- Initial identification of parcel boundaries including parcels intersected by 300-ft buffer applied to project ESL.

- Collect existing on-site data using conventional survey or GPS equipment to locate wells,

culverts, fences, pipelines, powerlines, and other existing components and infrastructure.

- Map location of proposed design features and organize the areas using the following identifiers:

  - Access Routes (A)

  - Contractor Use (C)

  - In-Channel (IC)

  - Riparian (R)

  - Upland (U)

  - Wetland/Pond (W)

  - River Crossing (X)

- Field validate existing topographic Digital Terrain Model (DTM) at key design locations

including proposed entrances of side channels, grade controls, split flow channels, etc. to determine overall design feasibility.

- Initial identification of potential save trees – digitized and provided to Design Groups

- Jurisdictional wetlands delineated and provided to Design Groups by CEQA contractor

- Conceptual Design Report

- Written project summary including: existing information, proposed design features, overall

project goals and objectives, and anticipated evolution of each design component.

- Report will contain appendix of the following information (maps and drawings will be AutoCAD

format using supplied TRRP design template):

- Plan maps of existing features (topography, aerials, and existing components)

- Plan maps of proposed design features (IC, R, U, and C areas)

- Existing condition profiles and cross-sections through proposed design features, utilizing

existing topographic DTM.

- Initial quantity calculation (area x average depth) summary information

- Initial cost estimation

Unit cost by volume applied to initial quantity calculation

Estimated Unit Cost Cut ($/CY)

Estimated Unit Cost Engineered Fill ($/CY)

Large wood materials applied to habitat type (e.g., wood, riparian), summarized in table.

- Digital information disc of all data including: field survey/GPS data, AutoCAD files, GIS

shapefiles, PDF map files, and digital copy of conceptual report)

  - Develop recommendations for Revegetation Designs

- Conceptual Design Phase (30% Design) Deliverables

- Deliver conceptual design report in electronic and hard copy format using three ring binder with

appendices and digital information disc to the TRRP office.

- Formal presentation of conceptual design report at the TRRP Design Team meeting.

## Multi-Disciplinary Review & Value Engineering Phase

Projects with initial cost estimations exceeding $1M will be required to undergo a Value Engineering Phase.

- Conceptual Design Reports, maps, and drawings will be reviewed by program partners and potentially other technical experts.

- Conceptual Design Reports, maps, drawings, and review comments will be provided to a value engineering study consultant.

- Value engineering study will be performed to develop a preferred alternative from the two alternatives of the Conceptual (30%) Design phase and VE study, and the accountability report will be prepared by the Implementation Branch Chief in consultation with applicable designers. Selection process for multi-disciplinary review team.

- If there are any unresolved issues or concerns at this point, a dispute resolution consultant will be

brought in to resolve them.

## Initial Engineering Design Phase (60% Design)

- Refine concepts

- Incorporate into initial design all TRRP partners formal comments after two-week review period.

Only comments received in writing will be accepted.

- Incorporate into initial design all comments and findings after formal Value Engineering (VE)

study is completed by multi-disciplinary review team.

- Design Team meeting to discuss VE Study results and USBR Accountability Report.

- Identify any additional upland areas for spoil locations meeting constraints to federal vs. non-federal minerals and make adjustments to the preferred alternative design to ensure cut fill equilibrium is achieved.

- Refine recommendations for Revegetation Designs

- Topographic Surveying

- Perform topographic survey of project site using survey grade GPS or conventional survey

equipment. Utilize established primary control point locations and values set by the California

Department of Water Resources (DWR). Surveys will be conducted in California State Plane,

Zone 1, NAVD88 or Geoid09 Datum.

- Concentrate topographic survey data collection in areas where the 2009 LiDAR DTM is

inaccurate. Perform validation ground truthing of existing topographic data obtained from 2009

LiDAR DTM to check topographic accuracy.

- Collect enough survey data including breaklines at key features to develop an accurate

one foot contour map of the existing ground surface. Specific locations are based on the designer discretion.

- Surface Model Development

- Build existing ground surface model using both point cloud data from 2016 LiDAR and on-site

topographic surveys. Surface model will have the accuracy of generating one foot contour map of

the project site. Surface model will be developed using AutoCAD Civil 3D TIN (Triangulated

Irregular Network) format.

- Develop initial design surface model of approved conceptual design features. Build conceptual

design features into a three-dimensional surface using grading tools to daylight into the existing

ground surface model. Surface model will be developed using AutoCAD Civil 3D TIN format.

- Hydraulic Validation and Analysis

- Perform field validation of flood frequency flows at project site using staking or real-time

surveying methods to establish an elevation of inundation at key hydrograph flow benches. Onsite

validation data of various flows will help to calibrate the existing conditions hydraulic model.

- Develop both existing conditions and initial design conditions one dimensional hydraulic models

of the project reach. Use modeled TIN surfaces to generate both existing and initial design

condition cross-sections to develop hydraulic model.

- Perform initial hydraulic analysis using HEC-RAS software to determine if initial design surface

will raise or lower the base flood elevation of the FEMA 100-year flood event by more than one

foot (The Design Team Workgroups should begin phasing into use of SRH-2D for FEMA flood modeling where possible).

- Perform hydraulic analysis using SRH-2D to develop realistic FYFAM input. Identify spatial

distribution of egg masses and tadpole desiccation. Minor adjusts to the design to create suitable conditions for FYLF.

- Quantity Calculations

- Utilize existing and design surface models to perform volume calculations to

refine design cut and fill quantities using AutoCAD Civil 3D software.

- Perform iterations of balance calculations between excavated and upland features as not to exceed

footprint area, elevation, or hydraulic constraints.

- Separate fill quantities into two separate volume categories: clean course sediment gravel (half a

ft below summer baseflow elevation) and raw fill (all materials half a ft above the summer

baseflow elevation)

- Generate quantity calculation report with volume summary table and calculation methodology

- Cost Estimation

- Generate updated cost estimation report to include cost savings/increases from design revisions.

- Engineering Drawing Package

- Development of engineering drawing package (construction documents) and confirm all revisions from the 30% drawings were made using AutoCAD supplied TRRP design template

including the following information:

- Plan maps of existing features (topography, aerials, and existing components)

- Plan maps of refined design features (IC, R, U, W, WP and A, C, X areas) including design contours, access roads, staging areas, additional spoils, recreational river access, no access areas, etc.

- Plan maps should be plotted to proper scale for overview representation and detailed

views using approximately 50 scale or similar

- Existing and design condition profiles and cross-sections through initial design features, utilizing developed surface models through AutoCAD Civil 3D.

- Beaver Dam Analog (BDA), Large Woody Debris (LWD), Wood Placement (WP), Wood Jam (WJ), Habitat Wood (WH), Wood Racking, Structured Log Jam (SLJ), Engineered Log Jam (ELJ) location map

- Salvaged material such as willow clumps and large wood and installation location maps

- Other important figures or design details/typicals (e.g., Fuel Containment, Turbidity Curtain, Cofferdam, Heavy Equipment Crossing)

- Draft Engineering Design Report

- Written project summary including: existing information, hydraulic analysis, refined design

features, overall project goals and objectives and prediction of design component evolution.

- Report will contain an appendix with the following information:

- Construction drawing package

- Hydraulic analysis report

- Quantity calculation report

- LWD or ELJ quantity, bouncy, and structural calculation report

- Correspondence report detailing conversations between program partners, landowners, or

other important design input, including formal design comments.

- Digital information disc of all data including: field survey/GPS data, AutoCAD files, GIS

shapefiles, PDF map files, and digital copy of conceptual report)

- Initial Design Phase (60% Design) Deliverables

- Deliver draft engineering design report in electronic format with

appendices and supporting documentation to the TRRP office.

- Formal presentation of initial design report at the TRRP Design Team Workgroup meeting.

## Final Engineering Design Phase (90% Design) and Final Revegetation Design Phase (90% Design)

- Provide comments or input on other TRRP Design Team’s Draft Engineering Reports, as applicable

- Respond to TRRP Design Team and landowner review comments.

- Incorporate into final design or respond to TRRP partner’s formal comments after two-week

review period.

- Incorporate into final design all comments and findings after formal discussions and negotiations with private and public landowners.

- Topographic Surveying

- Collect additional survey data as needed

- Surface Model Development

- Refine existing surface model as needed

- Refine design surface model based on formal comments received during comment period

- Hydraulic Validation and Analysis

- Refine existing or design conditions hydraulic models as needed based on any changes to the

surface models.

- Develop FEMA certification letter with PE stamp certifying base flood elevation.

- Quantity Calculations

- Refine quantity calculations as needed based on changes to the surface models.

- Cost Estimation

- Refine cost estimation report based on cost savings/increases from design revisions.

- Refine cost estimation report to include revegetation design costs

- Engineering Drawing Package

- Refine engineering drawing package (construction documents) and confirm all revisions from the 60% drawings were made based on comments received during comment period and any changes to the surface models.

- Develop Access Plan identifying access following civil construction phase, revegetation phase, and decommissioning.

- Revegetation design drawing package

- Develop revegetation design drawing package (construction documents) to include recommendations for Revegetation Designs and SWPPP

- Final Design Report and Final Revegetation Report

- Refine initial design report to include all comments received during comment period and changes

to the underlying calculations or models.

- Draft Final Revegetation Report

- Final Design Phase Deliverables

- Deliver final design report in digital and hard copy format using three ring binder to the TRRP

office.

## 100% Engineering Design and Report and 100% Revegetation Design and Report

- Final 100% CAD Drawings (Engineering Design and Revegetation Design)

- Final 100% Design Report and Revegetation Report

- Addendum(s) to Final Design Report and Revegetation Report

- Final plant counts for each design area

- Figure showing distance from design surface to summer/fall low water