Relating flow, habitat, temperature, food ration, and drift of macroinvertebrates to salmonid smolt success.

Pre-proposal

N. Hemphill and W. Trush, and others

Abstract

Benthic Macroinvertebrates are an important component of the Trinity River ecosystem and are expected to change in response to our management actions, especially flow. By quantifying the flow-habitat relationship for major Benthic Macroinvertebrate (BMI) species, BMI habitat can be managed to promote food availability for juvenile salmonids as well as the ecological health of the Trinity River. Using a bioenergetics approach and information from the flow-BMI habitat relationship, the effect of flow on ration and juvenile growth can be modeled.

This approach helps managers to better understand the implications of flow on potential growth of juvenile salmonids. Ultimately the success from juvenile emergence to smolt is dependent on juvenile growth as well as on ecosystem capacity. The flow-ration relationship can indicate how to balance physical modification to improve habitat capacity with the necessary food availability to supply the existing or constructed habitat.

Introduction

One of the influences of dams on natural ecosystems is to remove disturbance and variation in flow.  Dams reduce the frequency, magnitude and duration of floods and reduce the effects of drought. Aquatic organisms in particular macroinvertebrates are adapted to a highly variable flow regime (Lytle and Poff 2004).  Macroinvertebrates are an important ecosystem component (Cardinale and Palmer 2002, Vannote et al. 1980, Vaughn 2010); as secondary producers they play an important role in food webs, transfer energy and biomass between primary producers and fish, and, bridging between primary producers and fish.   Macroinvertebrates influence many ecosystem functions and processes such as nutrient spiraling, decomposition, and primary productivity (Wallace and Webster 1996). Differences over time in river conditions can alter linkages among invertebrates and ecosystem functioning (Cardinale and Palmer 2002).  Due their short life cycle, importance in the ecosystem and sensitivity to changing habitat macroinvertebrates are thought to be an ideal trophic level to study to assess changes in ecosystems.

Functional groups (grazers, shredders, gatherers, filterers and predators) of macroinvertebrates influence different ecosystem processes.  Dams influence the relative proportions of these functional groups. Macro-invertebrate drift was sampled below two dams; and included a high diversity of Trichoptera, Diptera, Ephemeroptera, and Plecoptera (Tonkin et al. 2009). The proportion of Ephemeroptera, Plecoptera and Trichoptera (EPT) was 3–4 times higher in the unregulated section of the river, but overall densities were similar along the river (Tonkin et al. 2009). Percent EPT (Ephemeroptera, Plecoptera, and Trichoptera) was negatively correlated with substrate compaction and % boulder in the substrate composition (Tiemann et al. 2005). Habitat changes caused by dams may be the primary negative impact on macroinvertebrates (Lessard and Hayes 2003).   A productive and diverse benthic macroinvertebrate (BMI) community is important for maintaining stream ecosystem integrity under a regulated flow regime (Jowett  2007).

Management actions such as gravel augmentation can influence benthic macroinvertebrate functional groups. On the Mokelumne River invertebrate standing crop, density and functional group changed within weeks after gravel augmentation; peaking 12 weeks later (Merz and Chan 2005). However, low species diversity was observed, 3 species comprised over 61% of the organisms (Merz and Chan 2005).

Background

Stream ecologists agree that chironomids, Ephemeroptera, Trichoptera and stoneflies are a good group to evaluate the health of the ecosystem.  Rapid assessments are based on EPT the three good indicators of invertebrate community health.  I would add in chironomids as they are an important component of young fish diets.   These four taxomonic groups encompass a wide range of functional group: grazers, filterers, gatherers, predators and shredders.

On the Trinity River, the dipterans simuliidae and chironomidae dominated Chinook and steelhead diets in the past (Appendix C 1980).  Coho salmon consumed chironomids cladocera, mayflies, black flies and worms.  Very few Trichoptera were consumed by this species. In the American River, Chinook salmon and steelhead fed primarily on chironomids, baetids, and hydropsychids (Merz and Vanicek 1996). In the lower Mokelumne River, California, juvenile Chinook salmon fed on zooplankton, chironomid, hydroptilid, and hydropsychid pupae (Merz 2002a and b).

During  the period 1970-1980 (Appendix C 1980) the Trinity River, deep swift runs and pools did not support many invertebrates; the highest diversity and numbers were found in shallow (<10 inches deep) riffles composed of small rocks of two to four inches and velocities from 1-2 fps.  In 1980, the riffles near the hatchery were dominated by black fly larvae, with 3,636 per sample at the hatchery declining to 80 per surber sample at Lewiston Bridge. Coho appeared to select more mayflies than the other two salmonids. Exclusive of simuliids, the average number of invertebrates was 80 per square foot up near Lewiston Dam.  In the reach between Indian Creek and the confluence of the North Fork the number dropped to 45 invertebrates per square foot.

The 1980 (Appendix C 1980) study predicted that the density of invertebrates should significantly increase as the substrate was cleansed of fines.  Fine bed material storage has decreased through much of the TRRP domain (Gaeuman and Krause 2011).    We would predict a corresponding increase in the density, biomass and species composition of invertebrates associated with this change. In addition where we have changed a reach to include more inundated gravel bars we would predict that we would see higher numbers of invertebrates and a higher diversity.

Importance to the Trinity River Restoration Program

Our recent management actions have changed the flows, the type of substrate and the interactions between substrate and flow. These changes in flow and substrate influence invertebrate community structure and secondary productivity. As we anticipate change in the bed form, the reduction of fines and the increase in transport and deposition of coarse material we predict a corresponding quick response in the benthic macroinvertebrate community structure and function.

We predicted (IAP, 2009) that as channel complexity increased that fish growth rates, survival, and condition would correlate positively to increases in benthic macroinvertebrate production, species diversity and abundance.  Salmonids, especially steelhead and cutthroat trout derive most prey from drift of benthic macroinvertebrates (Elliot 1970, Wilzbach et al. 1986). In addition, terrestrial insects that fall into the drift can be a seasonally important food source that can provide a significant percentage of a trout’s annual energy intake (Saunders and Fausch 2007).

In this plan we focus first on the hypothesis that benthic macroinvertebrate (BMI) habitat throughout the Program area could be managed to optimize food availability (terrestrial and aquatic macroinvertebrate production) with respect to requirements of early life stage salmon and steelhead.  A bioenergetics model would be used to predict salmon growth rates in response to BMI productivity. Lastly we hope that by modeling the linkages between BMI productivity, growth and smolt to spawner ratios that we can demonstrate the importance of managing seasonal flows for BMI productivity to Program managers.

Assessments

Improving knowledge and predictions of ecological responses to flows can be achieved by coupling physical system models to ecological responses and (2) clarifying empirical relationships between flow and the desired ecological responses through monitoring of experimental flow releases (Shafroth et al.2010).  One of the first assessments in the Integrated Assessment Plan (IAP) proposed for macroinvertebrates was to estimate of the area of suitable habitat for benthic production at different flows.  Bioenergetics models will be used to estimate consumption of macroinvertebrates by salmon and to make predictions of salmon growth which can be compared to changes in size class over time. (e.g. Hayes et al. 2007,Railsback and Rose, 1999, Beauchamp et al.1989).   This assessment would focus on riffles as these are known to be areas of high productivity.

Objective 1: Establish desired ecological outcomes for promoting productive BMI habitat in the mainstem Trinity River to improve juvenile salmonid rearing and increase smolt success.

Task 1. Quantify magnitude, duration, frequency, and timing of the annual hydrograph for promoting high BMI riffle productivity under unimpaired streamflows.

Task 2. Quantify magnitude, duration, frequency, and timing of regulated annual hydrographs and identify significant hydrological changes relative to existing BMI riffle habitat availability and quality.

Objective.2: Develop methods for quantifying streamflow – BMI riffle habitat relationships and overall BMI riffle habitat abundance in the mainstem Trinity River from Lewiston to the North Fork confluence.

Task No.1. Establish physical criteria for quantifying productive BMI habitat appropriate for 1D and 2D hydraulic modeling, DHM, and HHTs (hydraulic habitat thresholds).

Task.2. Classify riffles by hydraulic unit and quantify riffle area under baseflow conditions from Lewiston to the North Fork or Klamath River confluence.

Objective.3. Quantify relationship between streamflow and productive BMI habitat quantity/quality through field measurement and hydraulic modeling.

Task.1. With the intensity of hydraulic monitoring and modeling underway above the NF, many riffle study sites can be selected for analyses without requiring significant additional fieldwork.

Task 2. Validation of the depths and velocities predicted from the hydraulic models may have been done in some cases or may require field work to validate.

A second assessment would provide linkages between predicted habitat productivity and invertebrate drift out of riffles in order to validate the predictions of the first assessment.  Once the number of riffles has been mapped, 10 riffles will be selected from those modeled.

Objective 4. Estimate BMI drift rate and validate productive BMI habitat suitability criteria.

Task.1. Drift rate estimation.

Task 2. Estimate prey availability.

A third assessment would link the productivity of the riffles to improving juvenile growth and smolt success. This assessment may take longer to accomplish as not all Trinity River specific data on the primary dependent variables of migration rate, species specific growth rates (SpGr) as a function of water temperature, ration level, and ration level as a function of streamflow are available. However, values from the literature can be derived for missing variables. Models have been used to predict effects of water velocity on prey capture rates and gross energy intake rates by juvenile coho salmon and steelhead (Piccolo et al. 2008). Values for costs of swimming, energy composition of food in the drift, energetic costs of obtaining food can be obtained from the literature (e.g Trudel et al. 2005). Diet relative to prey availability (Johnson and Ringler 1980), and relation to growth rate (Rosenfeld and Taylor 2009) can also be estimated from the literature. much data is available in the literature for steelhead  juveniles and smolt size has been tied to marine survival (e.g. Lum 2003). Temperature has an influence on consumption rates and growth of fish as well as on macroinvertebrate communities (Lessard and Hayes 2003).

Objective 5. Estimate importance of BMI productivity for improving juvenile salmonid growth and smolt success.

Task 1. Establish smolt-to-adult return (SAR) curves for steelhead, Coho, and Chinook smolts.

Task 2. Apply growth model for smolt out-migration period under present annual hydrographs using water temperature preferences of the species examined.

Task 3. Apply growth model for smolt out-migration under proposed annual hydrographs to evaluate smolt success.

Task 4.  Determine how much a smolt grows as it migrates from the upper Trinity to the Lower Trinity. How much greater is fork length (FL) (or ‘condition’) in the Lower Trinity at Willow Creek?

Task 4. SAR curves would be used to evaluate increase in success as a function of greater smolt length/condition.

Finally, we propose to synthesize findings to provide a test of the hypothesis that macroinvertebrate habitat throughout the Program area could be managed to optimize food availability (terrestrial and aquatic macroinvertebrate production) with respect to requirements of early life stage salmon and steelhead and to test the hypothesis that  the TRRP can (A) incorporate BMI productivity into managing magnitude, duration, frequency, and timing of streamflows and (B) stipulate channel rehabilitation guidelines addressing BMI productivity that will meet ROD objectives.  In addition we hope that by including the linkages to growth and smolt to spawner ratios that we can demonstrate the importance of managing for BMI productivity.

Literature Cited

Appendix C. 1980, Proposed Trinity River Fish and Wildlife Program Appendix C Fish and Wildlife Analysis Final Volume 2. United States Department of the Interior, Water and Power Resources Service..

Beauchamp D. A., Donald J. Stewart & G. L. Thomas 1989.Corroboration of a Bioenergetics Model for Sockeye Salmon, Transactions of the American Fisheries Society, 118:6, 597-607

Cardinale B J and M .Palmer. 2002. Disturbance Moderates Biodiversity-Ecosystem Function

Relationships: Experimental Evidence from Caddisflies in Stream Mesocosms. Ecology, 83: 1915-1927

Elliott, J. M. (1970), Diel changes in invertebrate drift and the food of trout Salmo trutta L.Journal of Fish Biology, 2: 161–165

Gaeuman, D. and A. Krause 2011. 2010 Bed-material sediment budget update, Trinity River, Lewiston Dam to Douglas City, California. Tech Report:TR-TRRP-2011-2.

Hayes, JW, NF Hughes and Kelly 2007. Process-based modeling of invertebrate drift transport, net energy intake and reach carrying capacity for drift-feeding salmonids. Ecological Modeling, 207:171-188

Johnson, J. H. ,N.H. Ringler  1980.Diets of juvenile coho salmon (Oncorhynchus kisutch) and steelhead trout (Salmo gairdneri) relative to prey availability. Canadian Journal of Zoology, 1980, 58:(4) 553-558.

Jowett I. G. & A.J. H. Davey (2007) Comparison of Composite Habitat Suitability Indices and Generalized Additive Models of Invertebrate Abundance and Fish Presence–Habitat Transactions of the American Fisheries Society: 136, pp. 428-444

Lessard J L. and D B Hayes. 2003. Effects of Elevated Water Temperature on Fish and

Macroinvertebrate Communities below Small Dams. River Research and Applications 19: 721-732.

Lum, J. L. 2003. Effects of Smolt Length and Emigration Timing on Marine Survival and Age at Maturity of Wild Coho Salmon (Oncorhynchus Kisutch) at Auke Creek, Juneau Alaska. Master’s Thesis. University of Alaska Fairbanks. Accessed online at: http://www.arlis.org/docs/vol1/B/52760038.pdf

Lytle, DA and Poff.  2004.  Adaptation to Natural Flow Regimes. Trends in Ecology and Evolution 19 94-100.

Merz, JE and  CD Vanicek, 1996.Comparative feeding habits of juvenile Chinook salmon, steelhead, and Sacramento squawfish in the lower American River, California. California Fish and Game 82: 149-159.

Merz JE 2002a. Seasonal Feeding Habits, Growth, and Movement of Steelhead Trout in the Lower Mokelumne River, California. California Fish and Game 88(3):95-111

Merz ,JE. 2002b. Comparison Of Diets Of Prickly Sculpin And Juvenile Fall-Run Chinook Salmon In The Lower Mokelumne River, California. Southwestern Naturalist 47:195-204

Merz JE,. and Chan 2005 Effects Of Gravel Augmentation On Macroinvertebrate Assemblages In A Regulated California River. River Research and Applications. 21: 61–74

Piccolo J J., N.F. Hughes and M. D. Bryant 2008.Development of net energy intake models for drift-feeding juvenile coho salmon and steelhead Environmental Biology of Fishes Volume 83, Number 3, 259-267

Railsback, S. F. and K. A. Rose. 1999. Bioenergetics modeling of stream trout growth: temperature and food consumption effects. Transactions of the American Fisheries Society 128:241-256.

Rosenfeld  JS, and J, Taylor . 2009. Prey abundance, channel structure and the allometry of growth rate potential for juvenile trout Fisheries Management and Ecology, 2009, 16, 202–218

Saunders W. C. and K.D. Fausch. 2007.Improved Grazing Management Increases Terrestrial Invertebrate Inputs that Feed Trout in Wyoming Rangeland Streams Transactions of the American Fisheries Society 136:1216–1230.

Shafroth P B, AC Wilcox, DA Lytle, J T. Hickey, DC Andersen, VB Beauchamp, A Hautzinger, LE. McMullen and A Warner 2010.  Ecosystem effects of environmental flows: modeling and experimental floods in a dryland river. Freshwater Biology (2010) 55, 68–85

Tiemann, JS  Gillette, DP Wildhaber, ML Edds, DR. 2005. Effects of Lowhead Dams on the Ephemeropterans, Plecopterans, and Trichopterans Group in a North American River

Journal of Freshwater Ecology 20:519-525.

Tonkin, J. D., Death, R. G. and Joy, M. K. (2009), Invertebrate drift patterns in a regulated river: dams, periphyton biomass or longitudinal patterns? River Research and Applications, 25: 1219–1231.

Trudel, M. S. Tucker, J. F. T. Morris, D. A. Higgs & D. W. Welch (2005): Indicators of Energetic Status in Juvenile Coho Salmon and Chinook Salmon, North American Journal of Fisheries Management, 25:1, 374-390

Vannote, RL. GW Minshall, KW Cummins, JR Sedell, and CE Cushing. 1980. The Rriver Continuum Concept. Can. J Aquat. Sci. 37: 130-137.

Vaughn CC. 2010.Biodiversity Losses and Ecosystem Function in Freshwaters: Emerging Conclusions and Research Directions BioScience 60: 25-35

Wilzbach M.A. ,K.W. Cummins and J.D. Hall 1986 Influence Of Habitat Manipulations On Interactions Between Cutthroat Trout And Invertebrate Drift. Ecology, 67(4) Pp. 898-911