## Summary
Summary by Program Activity | 2017 Actuals | 2018 Approved | 2019 Approved | 2020 Proposed
Program Administration | 2630630.82 | 3376546.13 | 3082467.55 | 3384918.9857
(Program Administration - salary retained with FWS) | 65000 | 77495 | 77495 | 77495
Rehabilitation Implementation | 7312639.47 | 5628191.82 | 7620499.37 | 5598043.2648
Science Program - includes transferred FWS tribal funds | 4623544.62 | 5233615.42 | 3457425.08 | 4428037.7445
(Science Program - salary/ops funds retained with FWS) | 917809 | 1186440.52 | 1115497 | 1115497
TOTAL TMC Budget minus FWS salaries/ops | 14566814.91 | 14238353.37 | 14160392 | 13410999.9951
TMC Budget (minus FWS retained salaries/ops funds): | 2017 | 2018 | 2019 | 2020
USBR (Water & Related A30 funds) | 12030000 | 12197000 | 11911000 | 11911000
USBR (CVPIA H37 funds) | 1500000 | 1500000 | 1500000 | 1500000
FWS - annual transfer to USBR* | 613514 | 478487 | 749392
TOTAL | 14143514 | 14175487 | 14160392 | 13411000
*FWS annual funds transferred to USBR for Tribal monitoring/survey projects. Obligated with FWS prior FY end-of-year funds.
FWS TRRP Funds outside of TMC Budget* | 2017 | 2018 | 2019 | 2020
TOTAL FWS retained TRRP funds - salary/ops | 982809 | 1263935.52 | 1192992 | 1192992
*FWS funds retained at FWS annually; not part of expenditures approved by TMC

## Admin
PROGRAM ADMINISTRATION |  | 2017 Actuals | 2018 Adjusted Approved | 2018 Actuals | 2019 Approved | 2020 Proposed
TRRP Administration Personnel
TRRP Program Office Personnel ED, Secretary, Indian Self-Determination Specialist, Grants and Agreements Specialist |  | 650108.71 | 640516.4 |  | 674276.41 | 694504.7023
Reclamation Regional Office Personnel Contracting |  | 173982 | 190000 |  | 179201.46 | 179201.46
Reclamation Northern California Area Office Personnel (IT, maintenance, electricians, phone tech) |  | 94980 | 30000 |  | 97829.4 | 97829.4
FWS Administration personnel |  | 0 | 77495 |  | 77495 | 77495
| Subtotal | 919070.71 | 938011.4 | 0 | 1028802.27 | 1049030.5623
TRRP Administration
TRRP Program Office Operations (TRRP office rent, vehicles, security, utilities, supplies) |  | 379890 | 546898.44 |  | 515220 | 530676.6
TRRP Annual Report (BOR Denver TSC) |  | 0 | 47844 |  | 0 | 0
TMC Notetaker - TRRP contract |  | 23200 | 31926 |  | 15274 | 21948.4
Public Education and Outreach/Website - TCRCD Work expands community knowledge of Program and educates schoolchildren, promoting environmental stewardship with a goal of improving support/success of restoration efforts. |  | 130894 | 125219 |  | 131316 | 139218.35
| Subtotal | 533984 | 751887.44 |  | 661810 | 691843.35
Trinity Management Council
NOAA Fisheries - IA |  | 47000 | 97000 |  | 0 | 48500
Forest Service - IA |  | 73000 | 100000 |  | 0 | 50000
Hoopa Valley Tribe - AFA |  | 117919 | 124928.52 |  | 150785 | 157570.325
Yurok Tribe - AFA |  | 119298 | 122454 |  | 134389.27 | 138420.9481
CA Dept of Fish & Wildlife - FA |  | 33017 | 81917 |  | 85239 | 87796.17
CA Dept of Water Resources - FA |  | 79660 | 129320 |  | 0 | 64660
Trinity County -FA |  | 6745.71 | 6745.71 |  | 7112.11 | 7325.4733
| Subtotal | 476639.71 | 662365.23 |  | 377525.38 | 554272.9164
Technical Assistance
Hoopa Valley Tribe -AFA |  | 338950 | 350909.06 |  | 425934 | 445101.03
Yurok Tribe-AFA |  | 278987 | 386249 |  | 417640.9 | 430170.127
CDFW -FA |  | 0 | 189022 |  | 198250 | 204197.5
NOAA Fisheries - IA |  | 82999.4 | 175597 |  | 0 | 87798.5
Refinements Facilitator placeholder estimate - BOR |  | 0 | 0 | 0 | 50000
| Subtotal | 700936.4 | 1101777.06 |  | 0 | 1167267.157
TOTAL PROGRAM ADMINISTRATION |  | 2630630.82 | 3454041.13 |  | 3159962.55 | 3462413.9857
Partial or full 2-year funding, FY18 and FY19

## Rig
IMPLEMENTATION & WATERSHED BUDGET |  | 2017 | 2018 | 2018 | 2019 | 2020
|  | Actuals | Adjusted Approved | Actuals | Approved | Proposed
Implementation Personnel
TRRP Program Office Personnel (Implementation Branch Chief, Outreach Coordinator, Surveyor, Civil Engineer, Senior Natural Resource Specialist) |  | 1108859.59 | 865424.22 |  | 897053.18 | 923964.7754
| Subtotal | 1108859.59 | 865424.22 |  | 897053.18 | 923964.7754
Miscellaneous
FEMA/Flood Compliance Updates - Denver TSC |  | 39500 | 138000 |  | 0 | 69000
Trinity County Technical Assistance (TRRP grant, floodplain development permit, FEMA) |  | 35119.59 | 35126.72 |  | 35683.3 | 35800
Junction City House (estimate for elevation) |  | 0 | 0 |  | 200000 | 0
Realty Acquisitions (Easements, material storage) |  | 39067 | 36025 |  | 50000 | 50000
| Subtotal | 113686.59 | 209151.72 | 0 | 285683.3 | 154800
Planning
NEPA/CEQA Compliance/Permits/ (TRRP contract, wetland delineation, bird surveys, native seed, cultural res surveys) |  | 571941 | 438728 |  | 401890 | 413946.7
BAs Development (TRRP contract, spotted owl/coho/watershed wide) + $39k actual contract bid |  | 0 | 75000 |  | 39157 | 40331.71
Native Seed Supply |  | 0 | 0 |  | 0 | 0
BLM Technical Assistance - IA (NEPA, permits) |  | 57055 | 119294 | 119302 | 10000 | 0
BLM Wood Harvesting Agreement purchase of trees |  | 0 | 0 |  |  | 0
Geo-Physical Support Services
~As-Built Survey for Channel Rehab (FY19 funding for FY19 work and new contract also starting in FY19) |  | 105000 | 0 |  | 200000 | 0
~Summer Aerial Photography of 40 Miles |  | 35000 | 40000 |  | 50000 | 36062.17
~Property Boundary Surveys |  | 50000 | 49709 |  | 50000 | 23342.3
~Bathymetry, Aerial Lidar and Data Assembly (Funded Every 5 Years) |  | 135500 | 0 |  | 0 | 0
Map and Quantify Riparian Vegetation |  | 48079 | 0 |  | 0 | 0
TRRP-2018-008: Riparian Bird Monitoring |  | 36292 | 0 |  | 0 | 0
Herpetological Monitoring |  | 0 | 0 |  | 0 | 0
| Subtotal | 1038867 | 722731 | 119302 | 751047 | 513682.88
Design and Support Services
Hoopa Valley Tribe Support Services |  | 196800 | 242704 |  | 183742 | 192010.39
Yurok Tribe Support Services |  | 235578 | 242037 |  | 282246.94 | 290714.3482
CA Dept of Water Resources Support Services |  | 111430 | 170559.28 |  | 0 | 100219.28
USFS Technical Assistance Design, lg. wood/NEPA |  | 87891.29 | 227875.61 |  | 0 | 113937.81
TSC Design support OR Gulch |  | 0 | 35000 |  | 0 | 0
| Subtotal | 631699.29 | 918175.89 | 0 | 465988.94 | 696881.8282
Construction
Construction Projects - available funding |  | 3914826 | 713419 |  | 4240228.39 | 2320000
Value Engineering Study - Reclamation requirement |  | 0 | 40000 |  | 40000 | 40000
Sky Ranch and Sawmill road repair construction costs |  | 0 | 67675 |  | 0
Rehab Site Enhancements |  | 0 | 114000 |  | 0
BOR Willows Construction Office Inspection Services |  | 7776 | 0 |  | 125000 | 100000
Large Wood Supply YT |  | 199982 | 391000 |  | 0
High Flow Gravel Augmentation YT |  | 79993 | 116840.95 |  | 119814.93 | 123409.3779
Gravel/Coarse Sediment Processing/Placement YT |  | 150000 | 450000 |  | 0 | 150000
Revegetation Maintenance/Irrigation-HVT 3-year cycle for planning irrigation/maintenance, this is for sites planted during the previous 3 years. In FY 18 maintaining 3 sites- Bucktail, SC, and DG. |  | 66950 | 68958.5 |  | 72061.63 | 75304.4033
Geologic Investment (Test Pits) MP Region |  | 0 | 50000 |  | 0 | 0
Systemic Riparian Mapping Project HVT (Funded Every 5 Years) |  | 0 | 0 |  | 123622 | 0
| Subtotal | 4419527 | 2011893.45 | 0 | 4720726.95 | 2808713.7812
Watershed Implementation
Watershed FOA |  | 0 | 479455 |  | 500000 | 500000
Watershed FOA FY17 |  | 0 | 521579.82 |  | 0 | 0
| Subtotal | 0 | 1001034.82 |  | 500000 | 500000
TOTAL IMPLEMENTATION BUDGET |  | 7312639.47 | 5728411.1 |  | 7620499.37 | 5598043.2648
Amounts are 2-year funding, FY18 and FY19

## Science
SCIENCE BUDGET |  | 2017 | 2018 | 2018 | 2019 | 2020
|  | Actuals | Adjusted Approved | Pay Forward FY19 costs | Approved | Proposed
Science Program Support
TRRP Program Office Personnel (Data Steward, Hydrologist, Geomorphologist, Natural Resource Specialist) |  | 732854.88 | 693608 |  | 727397.03 | 749218.9409
TRRP Program Office Personnel (HVT) - Riparian Ecologist |  | 135740 | 144000 |  | 179320 | 187389.4
FWS Science Personnel (FY19 $882,445) portions of Supervisory Fish and Wildlife Biologists, Supervisory Fish Biologists, and Fishery technicians positions, and Office Operations (FY19 $233,052) |  | 917809 | 1186440.52 |  | 1115497 | 1148961.91
SAB Participation (5 SAB members) moving $115k from FY19 to FY20 |  | 73214.79 | 74497.94 |  | 0 | 115000
Reviews (Program science reports peer reviews-FWS) |  | 0 | 0 |  | 15000 | 15000
| Sub-total | 1859618.67 | 2098546.46 |  | 2037214.03 | 2215570.2509
Science Synthesis Reports
Fully funded in FY18 | Sub-total | 0 | 570377.34 |  | 0 | 0
Status and Trend Monitoring: Adaptive Management
TRRP-2018-014: Monitor redd distribution, abundance and densities CDFW, YT, HVT, FS, FWS |  | 257849.95 | 320203.15 | 58872 | 225518.45 | 292277.88
California Department of Fish and Wildlife |  | 47944.61 | 92795.31 | 47083 | 0 | 48495.49
Yurok Tribe |  | 76295.88 | 72312.55 | 4522 | 69779.19 | 74436.85
Hoopa Valley Tribe |  | 80269 | 83362.55 | 0 | 96606.2 | 100953.479
Forest Service |  | 0 | 14322 | 7267 |  | 7485.01
Fish and Wildlife Service |  | 53340.46 | 57410.74 | 0 | 59133.06 | 60907.0518
TRRP-2018-012:Outmigrant Monitoring HVT, YT, FWS |  | 751904 | 799873.82 | 44407.82 | 799673.33 | 831552.6899
Hoopa Valley Tribe |  |  | 455772.52 |  | 525944 | 549611.48
Yurok Tribe |  |  | 250901.02 | 44407.82 | 221798.43 | 228452.3829
Fish and Wildlife Service |  |  | 48792 |  | 51930.9 | 53488.827
TRRP-2018-030: ~Gravel Implementation Monitoring (TRRP contract) |  | 102000 | 214870 | 109300 | 0
TRRP-2018-036: Stream Gaging BOR Region Contract |  | 234000 | 244850 |  | 265600 | 273568
| Sub-total | 1345753.95 | 1579796.97 | 212579.82 | 1290791.78 | 1397398.5699
Effectiveness Monitoring
TRRP-2018-035: Channel rehab habitat effectiveness (YT, HVT, FWS) pending peer review |  | 89870 | 137189.89 |  | 175000
Yurok Tribe |  |  | 27714.77
Hoopa Valley Tribe |  |  | 49985.57
FWS (IP TSC contract missed FY18 funding-BOR to fund) |  |  | 59489.55 |  | 36000
TRRP-2018-023: Riparian Recruitment (HVT) |  | 0 | 63229 |  | 0
TRRP-2018-028: Soil Amendments (HVT) |  | 0 | 26345 |  | 0
|  |  | 26345 |  | 0
TRRP-2018-029: Macroinvertebrate Drift (YT, HVT) pending peer review |  | 0 | 183713 |  | 174885
Yurok Tribe |  |  | 145580 |  | 139580
Hoopa Valley Tribe |  |  | 38132 |  | 35305
| Sub-total | 89870 | 410476.89 |  | 385885 | 0
Model/Research
TRRP-2018-013: S3 Model (FWS, USGS, YT, HVT) |  |  | 74426 |  | 0
Fish and Wildlife Services |  |  | 0
United States Geological Society |  |  | 63466
Yurok Tribe |  |  | 1346
Hoopa Valley Tribe |  |  | 9614
TRRP-2018-020: Riparian Recruitment Model (HVT) |  | 0 | 77742 |  | 0
| Sub-total | 0 | 226594 |  | 0 | 0
Status and Trend: Fishery Management/Monitoring
TRRP-2018-034: Chinook Coded Wire Tagging-Fall Chinook NCAO paying CWT purchase $114k (HVT) |  | 150470 | 164000 |  | 189413.47 | 197937.0761
TRRP-2018-001: Chinook Run-Size Est.(CDFW, HVT) |  | 646160 | 827646.28 | 393653 | 68445.84 | 476988.49
California Department of Fish and Wildlife |  | 588852 | 768561.77 | 393653 | 0 | 405462.59
Hoopa Valley Tribe |  | 57308 | 59084.51 |  | 68445.84 | 71525.9028
TRRP-2018-015: Video Weir WC (CDFW, HVT, YT) |  | 0 | 84162 |  | 0 | 0
California Department of Fish and Wildlife |  | 0 | 32563.59 |  | 0 | 0
Hoopa Valley Tribe |  | 0 | 40819.2 |  | 0 | 0
Yurok Tribe |  | 0 | 10779.21 |  | 0 | 0
TRRP-2018-026: YT Harvest (Lower Klamath) (YT) |  | 160000 | 120000 |  | 160000 | 180000
TRRP-2018-006: HVT Harvest (Lower Harvest)(HVT) |  | 86552 | 93273 |  | 112751.56 | 117825.3802
TRRP-2018-010: State Lower Klamath (CDFW) |  | 99170 | 70084 |  | 98119 | 101062.57
TRRP-2018-004: Fall Run Scale Age (HVT, YT) |  | 111681 | 114786 |  | 134400.89 | 139773.94
Hoopa Valley Tribe |  | 70865 | 73970 |  | 89401.66 | 93424.7347
Yurok Tribe |  | 40816 | 40816 |  | 44999.23 | 46349.2069
TRRP-2018-005: Sport Harvest/Trinity Creel** HVT |  | 74269 | 60313 |  | 95900.51 | 100216.0329
| Sub-total | 1328302 | 1534264.28 | 393653 | 859031.27 | 1930565.9237
Total Science Budget |  | 4623544.62 | 6420055.94 | 1709398.46 | 4572922.08 | 5543534.7445
Partial or full 2-year funding; 25% Reduction due to 2017 low fish return; Actual Amount Unknown, Copied Estimate from FY17 Approved budget;